## ITP Page 1
INSPECTION AND TEST PLAN (ITP)
Customer: |  | Energy Infrastructures (PEI) | [7 empty] | Unit:
Location: |  | ASHDOD, ISRAEL | [7 empty] | Doc.No.: |  | 165900-PR-SP-005 |  |  | Appendix E
Project: |  | 165900 VOC TREATMENT SYSTEM | [7 empty] | Page No.: |  | 1 | of | 2 | Rev.: | P0
- THE «ITP» IS A GUIDELINE DEFINING THE EXTENT OF CONTRACTOR AND OWNER/OWNER REPRESENTATIVE FOR ALL INSPECTION LEVELS
- TYPE AND EXTENT OF TESTS SHALL COMPLY WITH CODES AND/OR ORDER SPECIFICATIONS
EQUIPMENT DESCRIPTION: |  |  |  |  | VOC treatment system
CRITICALITY RATING: | [5 empty] | INSPECTION LEVEL: |  |  | 1 |  |  | MR CODE:
VENDOR: | [7 empty] | INSPECTION AUTHORITY:
REMARKS:
1. | SCOPE
This Inspection and test plan is an engineering document which defines for each type of equipment:
The type and extent of Contractor and Owner/Owner Representative involvement in each phase of fabrication, control and testing requiring an inspection.
The resulting Suppliers contractual obligations, in accordance with applicable Project General Purchase Conditions.
| Note: | The inspection and test plan may under no circumstances be used as a substitute for the Suppliers Quality Control Plan.
2. | DEFINITION OF LUDAN / PEI
The nature of LUDAN/PEI involvement is indicated against each activity of fabrication and testing by means of the letters, H, W and R the meaning of which is the following:
| H: | (Hold) Point
The Supplier cannot carry out the specified controls and tests without Inspector attendance.
Consequently, the attendance to witnessing is mandatory. The Supplier must notify PEI by E-MAIL of the dedicated inspection activity at least fifteen (15) days in advance.
The Supplier cannot deviate from this rule unless written approval has been given by involved operating center.
| W: | (Witness)
The Supplier must notify PEI of the dedicated inspection activity at least fifteen (15) days in advance. PEI representative witnessing is not mandatory, but optional. When a percentage value is indicated (i.e. W 10%) the inspection activities will be witnessed on spot basis as per percentage indicated.
If PEI representative does not elect to be present, the Supplier may proceed with his own inspection, provided controls and tests records are made available to Inspector for review.
PEI and/or its authorized representative shall have the right to inspect equipments at any time during fabrication and tests to be assured that the equipments materials and workmanship are in accordance with this specification
| R: | (Review) - Review of Documents
The Supplier has either to submit to Inspector for comments the documents required prior to the performance of the dedicated activity or to transmit or make available for the review of Inspector the results of the controls and tests conducted, as the case may be.
3. |  | SUPPLIER’S FABRICATION AND QUALITY CONTROL PLAN
The Supplier must issue a Fabrication and Quality Control Plan for each item of equipment.
The Supplier’s Fabrication and Quality Control Plan is a document which defines in a chronological manner the list of the operations of fabrication, controls and tests in accordance with his own “know-how” and with the requirements specified in Material Requisition.
Following information shall be clearly specified against each operation:
|  |  | - | Reference documents (drawings, procedures, etc.)
|  |  | - | Acceptance criteria (code, etc.)
|  |  | - | Recording documents for controls and tests
|  |  | - | Involvement of the Quality Control department of the Supplier and/or his subsupplier
This Supplier’s Fabrication and Quality Control Plan will have to include all inspection activities defined in Inspection and Test Plan as well as all inspection activities scheduled by the Independent Inspection Authority and/or the Client.
For equipment of inspection levels 1, 2 and 3, the Supplier’s Fabrication and Quality Control Plan will have to be submitted compulsory to PEI for comments before the pre-inspection meeting is held.
4. |  | INSPECTION RELEASE CERTIFICATE
This document issued by PEI third party inspector, permits the Vendor to proceed with the packing and to notify the shipment
P0 | FOR COMMENTS | [5 empty] | 16.09.24 | B.S. |  |  | E.H. |  |  |  | M.SH.
Rev. | Status | [5 empty] | Date | Written by |  |  | Checked by |  |  |  | Approved by/Authorized by
DOCUMENT REVISIONS

## ITP Page 2
INSPECTION AND TEST PLAN (ITP)
Customer: |  | Energy Infrastructures (PEI) | [7 empty] | Unit: |  | 0
Location: |  | ASHDOD, ISRAEL | [7 empty] | Doc.No.: |  | 165900-PR-SP-005 |  |  | Appendix E
Project: |  | 165900 VOC TREATMENT SYSTEM | [7 empty] | Page No.: |  | 2 | of | 2 | Rev.: | P0
- THE «ITP» IS A GUIDELINE DEFINING THE EXTENT OF CONTRACTOR AND OWNER/OWNER REPRESENTATIVE FOR ALL INSPECTION LEVELS
- TYPE AND EXTENT OF TESTS SHALL COMPLY WITH CODES AND/OR ORDER SPECIFICATIONS
CLASS: |  |  |  | TYPE: | VOC treatment system | [8 empty] | MR:
INSPECTION
LEVEL
STAGE | A C T I V I T I E S |  |  |  | 1 | 2 | 3 | 4 | 5 |  | REQ. OF CERTIF. | APPLICABLE DOCUMENTS
| D E S C R I P T I O N | [10 empty] | AND REMARKS
BEFORE FABRICATION
| Preinspection Meeting |  |  |  | H | H | H |  |  |  | -
| Suborders Check |  |  |  | R | R | R | R |  |  | - | For main materials and/or activities complete with all the technical attachments
| Welders and N.D.E. operators qualifications |  |  |  | R | R | R | R |  |  | YES
| Welding consumable certificates |  |  |  | R | R | R | R |  |  | YES
| Material test certificates |  |  |  | R | R | R | R |  |  | YES
| Inspection of sub-ordered components |  |  |  | W | W |  |  |  |  | - | To verify correct marking against certificates, surface condition, thickness, etc.
| N.D.E. on raw materials |  |  |  | W | W | R | R |  |  | YES | If required
DURING FABRICATION | Check of the correct assignment of the materials and relevant certificates |  |  |  | H | W | R | R |  |  | YES | As soon as assigned to the specific item - Location map is requested
| Marking transfer |  |  |  | W | [5 empty] | -
| Fit-up |  |  |  | W | [5 empty] | - | To verify correct application of welding and fabrication procedure and bevels preparation
| Check of formed heads / headers |  |  |  | W | W | R | R |  |  | YES | As soon as available
| Shell and heads thickness check |  |  |  | W | W | R | R |  |  | YES | As soon as available
| Weld repairs (if any) |  |  |  | H | W | R | R |  |  | YES | To be recorded
| Intermediate N.D.E. |  |  |  | W | R | R | R |  |  | YES
| External and internal visual and dimensional check |  |  |  | H | W | W | R |  |  | YES | Before PWHT
| PWHT - Check of positioning of the pieces, location of thermocouples and calibration of the necessary devices |  |  |  | H | W | R | R |  |  | YES | Recorded chart and calibration certificate is requested
| X-Rays inspection |  |  |  | R | R | R | R |  |  | YES | Film review - Location map is requested
| Final N.D.E. |  |  |  | W | W | R | R |  |  | YES
| Hardness test of welds |  |  |  | H | W | R | R |  |  | YES
| Mechanical test of production coupons |  |  |  | H | W | R | R |  |  | YES
| PMI |  |  |  | H | W | W | R |  |  | YES | Only if specifically required
FINAL TEST | Pneumatic test |  |  |  | W | W | W | R |  |  | YES | For reinforcing pads
| Internal and external visual check |  |  |  | H | W | W | W |  |  | -
| Dimensional check |  |  |  | H | W | W | W |  |  | YES | As built sketch to be provided
| Hydraulic test |  |  |  | H | W | W | R |  |  | YES
| Nameplate check & C E marking check |  |  |  | W | W | R | R |  |  | YES
| Surface preparation/painting check |  |  |  | W | W | W |  |  |  |  | To check correspondence and quantity of loose materials as spares, internals (if not installed) etc.
| Loose material check |  |  |  | H | W | W | R |  |  | YES | If any
DOCUMENTATION
| Quality Control Manufact. Dossier check |  |  |  | H | H | H | H | H |  | - | As per 165900-PR-SP-007