## VDDR
Appendix "F" VENDOR DRAWINGS AND DATA REQUIREMENTS (VDDR)
Project number: |  | 165900 |  |  | Doc.No.: | 165900-PR-SP-006
Project name: |  | VOC TREATMENT SYSTEM |  |  | Rev. | P0 | By: | BS
Client: |  | Energy Infrastructures (PEI) |  |  | Date: | 16.09.2024 | App.: | M.SH.
Equipment : |  |  | VOC TREATMENT SYSTEM
Document title | Project document number | Submit with Proposal (Y or N) | APPROVAL DUE DATES |  |  | CERTIFIED DUE DATES (not required if no date is noted) |  |  | Remarks
|  |  | Requested date (ARO) | Vendor proposed date (ARO) | Agreed date (ARO) | Requested date (ARAD) | Vendor proposed date (ARAD) | Agreed date (ARAD)
Vendor Document Index and Schedule |  | Y | 2 wks
Engineering, Procurement, Manufacture, Delivery, Fabrication and testing Schedule |  | Y | 2 wks
Monthly Progress Report (On-Going, Monthly) |  | N | 4 wks
Delivery, Handling and Packing Proposal |  | Y | 2 wks
Sub vendor and main supplier list |  | Y | 2 wks
Relevant Project Reference List |  | Y | 2 wks
General arrangement drawing with weights and centers of gravity, including foundation/structure loading information |  | N | 4 wks |  |  | 2 wks
List of costumer Connections corresponding to P&ID |  | N | 4 wks
Cross-sectional drawing and bill of materials |  | N | 4 wks |  |  | 2 wks
Detailed Fabrication Drawings |  | N | 8 wks |  |  | 2 wks
Lifting lugs details / Calculations |  | N | 8 wks |  |  | 2 wks
Slinging/Lifting Arrangement and/or Strategies |  | N | 6 wks |  |  | 2 wks
Transport & Lifting Drawings with Centre of Gravity & Weights |  | N | 6 wks |  |  | 2 wks |  |  | including protection required during transportation
Erection instructions & Associated Drawings |  | N | 6 wks |  |  | 2 wks
Surface Preparation and Paint system specification |  | N | 4 wks |  |  | 2 wks
Design calculations - Thermal |  | N | 4 wks |  |  | 2 wks
Design Calculations -Pressure/Mechanical |  | N | 4 wks |  |  | 2 wks
Bolting and Gaskets Schedule |  | N | 8 wks |  |  | 2 wks
Bolt Torque Schedule |  | N | 8 wks |  |  | 2 wks
Maximum Allowable Nozzle Loads, include on GA drawing |  | N | 4 wks |  |  | 2 wks
QA & QC Plan |  | Y | 4 wks
Inspection and Test Plan |  | Y | 4 wks |  |  | 2 wks
Inspection and Test Program (Surveillance) on Sub Vendors |  | N | 4 wks
Welding Procedure Specifications & Welding Procedure Qualification Records |  | N | 14 wks | [5 empty] | Included in MDR
Welding Repair Procedures |  | N | 14 wks | [5 empty] | Included in MDR
Weld Map |  | N | 14 wks | [5 empty] | Included in MDR
Welders Qualifications |  | N | 14 wks | [5 empty] | Included in MDR
Non Destructive Exam procedures |  | N | 14 wks | [5 empty] | Included in MDR
Non Destructive Exam reports |  | N | 14 wks | [5 empty] | Included in MDR
Non Destructive Exam Operator Qualifications |  | N | 14 wks | [5 empty] | Included in MDR
Post Weld Heat Treatment procedure and records |  | N | 8 wks | [5 empty] | Procedures to be submitted for approval. Records to be included in MDR.
Leak/Hydrotest Procedures |  | N | 8 wks | [5 empty] | Procedures to be submitted for approval
Leak/Hydro Test Reports and Certificates |  | N | 14 wks | [5 empty] | Included in MDR
Bolt Tensioning Procedure |  | N | 8 wks
Material Certificates |  | N | 8 wks | [5 empty] | Included in MDR
Painting/Coating Records |  | N | 14 wks | [5 empty] | Included in MDR
Dimensional Report |  | N | 14 wks | [5 empty] | Included in MDR
Deviation Design Requests (Concession Records) |  | N | 14 wks | [5 empty] | Included in MDR
Client approved Non Conformance Reports |  | N | 14 wks | [5 empty] | Included in MDR
Installation, Operation and Maintenance Manuals Index |  | N | 8 wks |  |  | 4 wks
Installation, Operation and Maintenance Manuals (IOM) |  | N | --- |  |  | 6 wks Prior To shipment
Manufacturers Data Report Index |  | N | 8 wks
Manufacturers Data Report |  | N | --- |  |  | 2 wks after Shipment
Preservation & Storage Procedure (Short and Long Term) |  | N | 8 wks
Pressure Vessel - Design Registration Statutory Authority |  | N | --- |  |  | 4 wks before Shipment |  |  | required for customs clearance
Nameplate Details |  | N | 4 wks |  |  | 2 wks
Packing List |  | N | --- |  |  | 1 month before delivery |  |  | preliminary / final
Recommended List of Special Tools |  | Y | 4 wks
Recommended Commissioning Spare Parts List (Priced) |  | Y | 4 wks
Recommended 2 years Spare Parts List (Priced) |  | Y | 4 wks
Recommendations for protection during transportation |  | N | 8 wks | [5 empty] | with transportation and lifting drawing
NOTES:
1. Documentation submittal requires:
- Approval documents: (1) PDF or other specified format
- Certified final documents: (1) PDF (or other specified format), (1) Native document format (.dwg, excel, word)
2. ARO = after receipt of order
3. ARAD = after receipt of approval drawings
4. Where "Included in MDR" is shown, these documents must be made available to appointed Third Party Inspector for review and sign off.